## Product Backlog
Sword of Babylon
Description
Basic Hero runs and jumps
3D environment: All base BSP for Arena and Sandbox Room complete and gameplay relevant statics placed
Hero slashes sword to damage the boss
Boss attacks player using paw swipe and charge
Player sees basic character information: Health, Endurance, Boss Health
Basic Game Flow (Engine) works: player can start the level and reset on death
All Art Assets at Mockup Quality as definied in the ADP
Cinematic Storyboards Created: 4 Cinematics
All sounds found
Proof of Concept Tech
Final HUD in-game: Utilizes Shippable Quality Art Assets
Boss AI actively tracks and seeks out player to attack
Hero can roll-dodge to the left and right
Hero can lock-on to the enemy for attacks
Boss flies to the top of the center tree for second battle phase
Boss shoots Soul Orb Projectiles that track Mashu
Soul Orbs collide with Moon Orbs: destroy all six to advance
Shedu flies down from tree for third phase
Shedu more aggressive in third phase (faster attacks)
Arena feels like Hanging Gardens: Trim, Foliage, Column Meshes Complete
Game fully installs and runs off a standard DVD
Player views intro and transition to shadow realm cinematics
Basic Menu Navigation: Main Menu, Death, Pause
Interim Milestone (Design Test)
Final Hero in-game: Shippable Quality Model, Materials, and Animations)
Final Environmental Meshes: Tree, Frieze, Rubble
Play through from beginning to end without encountering any showstopper bugs or issues
Boss is balanced well: Player able to dodge successfully, trick the boss using the Juke Dodge, survive the fight
Player views shift from shadow mode cinematic
Final Installer: Installs game
First Playable
Final Boss in-game: Shippable Quality Model, Materials, and Animations)
Environment decorated to Art Style Guide Quality
Mashu controls balanced for maximum usability as a result of playtesting
Shippable marketing materials: DVD-cases, manual insert, DVD labels
Four (4) Master copies created and verified to be bit accurate
Archived on Network and on One (1) DVD
Alpha
Finished Game/Demo
Note on B38: In a real product backlog, items are more likely to be in the form of user stories. E.g. this item could be stated as "As a user I want to see the real weather data so that I could know what to wear before leaving home"

## Sprint Backlog Overview
Proof of Concept Tech |  |  | Interim Milestone 2 |  |  | Man-Hour Allocation
Backlog Actuals |  |  | Backlog Acuals |  |  | Team Overscope
March 29, 2010 to April, 8 2010 |  |  | April 8, 2010 to April 22, 2010 |  |  |  | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Total | Over Available Hours
[6 empty] | Loren | 18.5 | 46.5 | 11.5 | 10 | 86.5 | +/- 2 of Available Hours
| Estimated Hours | Available Hours |  | Estimated Hours | Available Hours | Tony | 23.75 | 21.5 | 5 | 12 | 62.25 | Under Available Hours
Programming | 53 | 54 | Programming | 78.5 | 72 | Ben | 15.5 | 19 | 10.5 | 9 | 54
Art | 29 | 36 | Art | 73.45 | 48 | Alex | 19.95 | 68.2 | 39 | 9.75 | 136.9
Level Design | 60 | 54 | Level Design | 62.5 | 63 | Robbie | 8.85 | 21.25 | 20.05 | 6.25 | 56.4
Sound | 6 | 0 | Sound | 3.75 | 0 | Rich | 26.5 | 25.5 | 17.25 | 13.5 | 82.75
Production | 37 | 18 | Production | 52 | 33 | Waylon | 19.95 | 15.75 | 10.75 | 11.5 | 57.95
Total Hours | 185 | 162 | Total Hours | 270.2 | 216 | Wade-Hahn | 25.5 | 25.5 | 35.5 | 22 | 108.5
[6 empty] | Chris | 25.25 | 26.75 | 29.75 | 16.75 | 98.5
| Actual Hours |  |  | Actual Hours
Programming | 75.5 |  | Programming | 78 |  | Avail Hrs | 18 | 24 | 24 | 12 | 78
Art | 43.75 |  | Art | 65.5
Level Design | 45.5 |  | Level Design | 61
Sound | 4 |  | Sound | 5.5
Production | 52.25 |  | Production | 42.75 |  | Total Estimated Hours |  |  | 745.25
Total Hours | 221 |  | Total Hours | 252.75 |  | Total Available Hours |  |  | 702
First Playable |  |  | Alpha |  |  | Man-Hour Actuals
Backlog Actuals |  |  | Backlog Actuals |  |  | Team Overscope
April 22, 2010 to May 6, 2010 |  |  | May 6, 2010 to May 13, 2010 |  |  |  | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Total
[6 empty] | Loren | 24 | 37 | 12 | 18.5 | 91.5
| Estimated Hours | Available Hours |  | Estimated Hours | Available Hours | Tony | 33.75 | 17.5 | 16 | 16 | 83.25
Programming | 18.5 | 53 | Programming | 19.5 | 20 | Ben | 27 | 30.5 | 13.5 | 8 | 79
Art | 47.55 | 48 | Art | 13 | 24 | Alex | 40 | 54.25 | 34.75 | 13 | 142
Level Design | 70.5 | 72 | Level Design | 28.25 | 28 | Robbie | 14.5 | 23.75 | 18.05 | 15 | 71.3
Sound | 3 | 3 | Sound | 2 | 2 | Rich | 19 | 16.25 | 20.5 | 13.5 | 69.25
Production | 39.75 | 40 | Production | 48 | 34 | Waylon | 11.75 | 19.5 | 20.5 | 10.75 | 62.5
Total Hours | 179.3 | 216 | Total Hours | 110.75 | 108 | Wade-Hahn | 21.5 | 26 | 22.5 | 9.5 | 79.5
[6 empty] | Chris | 29.25 | 28 | 25.5 | 15 | 97.75
| Actual Hours |  |  | Actual Hours |  | Team Total | 220.75 | 252.75 | 183.3 | 119.25 | 776.05
Programming | 30.5 |  | Programming | 23 |  | Avail Hrs | 18 | 24 | 24 | 12 | 78
Art | 42.75 |  | Art | 15
Level Design | 65.5 |  | Level Design | 16
Sound | 4 |  | Sound | 0
Production | 40.55 |  | Production | 65.25
Total Hours | 183.3 |  | Total Hours | 119.25

## Proof of Concept Tech
Sprint 1. Proof of Concept Tech
Not Finished/Moved to Next Milestone
days in sprint / effort left
| Tasks | Estimate | Actual | Accuracy | Priority | Assigned To: | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
[7 empty] | 183.75 | 187.75 | 156.8 | 127.05 | 75.45 | 54.5 | 70.5 | 21.25
Programming
Programming | Game loads white boxed level 1 | 1 | 1 | 100% | High | Loren | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Player character in game using temporary model | 3 | 3 | 100% | High | Tony | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Programming | Player character can move | 6 | 9 | 66.67% | High | Tony | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0
Programming | Player character can use the melee weapon | 6 | 7 | 85.71% | High | Tony | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
Programming | Shedu character in game using temporary model | 3 | 1 | 300% | High | Ben | 3 | 3 | 5 | 5 | 5 | 0 | 0 | 0
Programming | Shedu character in game using temporary model | 1 | 1.5 | 66.67% | High | Tony
Programming | Shedu character tracking to player | 5 | 5 | 100% | High | Ben | 5 | 3 | 1 | 1 | 0 | 0 | 0 | 0
Programming | Shedu character performing single melee attack | 5 | 5 | n/a | High | Ben | 5 | 5 | 5 | 5 | 4 | 4 | 2 | 1
Programming | Simple HUD displaying player and boss HP | 3 | 4 | 75% | High | Loren | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0
Programming | Game supports a level ending event resulting in a level reset | 6 | 4.5 | n/a | Med | Loren | 6 | 6 | 6 | 6 | 7.5 | 5.5 | 5 | 2
Programming | Player character has a melee weapon | 6 | 0 | 0% | Low | Tony | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
Programming | 3D Camera Movement | 3 | 4 | 75% | High | Tony |  | 3 | 1 | 0 | 0 | 0 | 0 | 0
Programming | Setup SVN | 6 | 2 | 300% | High | Loren | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Setup SVN | 1 | 2 | 50% | Med | Tony | bar: days in sprint / effort left 0 to days in sprint / effort left 7
Programming | Setup SVN | 1 | 2 | 50% | Med | Ben | bar: days in sprint / effort left 0 to days in sprint / effort left 7
Programming | Fix SVN | 1 | 0.5 | 200% | High | Loren | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Programming | Research UDK | 6 | 6 | 100% | Low | Loren | 0 | 6 | 3 | 0 | 0 | 0 | 0 | 0
Programming | SVN Support | 0.5 | 1 | 50% | High | Loren | days in sprint / effort left 4: 0; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Programming | Engine supports Game Type | 1 | 1 | 100% | High | Loren | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Programming | HUD shows Boss HP only when relevent | 1 | 1 | 100% | High | Loren | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Programming | Custom bones for Mashu | 2 | 1 | 200% | Med | Tony | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Programming | Shedu State and Decision System | 6 | 3.5 | n/a | High | Ben | days in sprint / effort left 4: 6; days in sprint / effort left 5: 4.5; days in sprint / effort left 6: 3.5; days in sprint / effort left 7: 3
Programming | PC can dodge | 6 | 3 | n/a | High | Tony | days in sprint / effort left 6: 6; days in sprint / effort left 7: 3
Programming | Shedu charge attack | 5 | 2.5 | n/a | High | Ben | days in sprint / effort left 6: 5; days in sprint / effort left 7: 2.5
Programming | Shedu Strafing | 6 | 5 | n/a | High | Ben | days in sprint / effort left 6: 6; days in sprint / effort left 7: 2
Art
Art | All BSP Material Texture Mockups | 0.7 | 0.25 | 280% | Med | Waylon | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | All BSP Material Texture Mockups | 0 | 0.25 | 0% | Med
Art | Brick Material (real world) diffuse Texture | 1 |  | 0% | High | Robbie | bar: days in sprint / effort left 0 to days in sprint / effort left 7
Art | All Mockup Environmental Meshes | 1 | 3 | 33.33% | Med | Robbie | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Art | All Column Meshes | 1.5 | 3.5 | 42.86% | High | Alex | 1.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Art | Column Mesh Unwrap | 0.75 | 1 | 75% | High | Alex | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0
Art | Column Base Mesh Unwrap | 0.75 | 0.75 | 100% | High | Alex | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 | 0
Art | Trim (variant 1) Mesh Unwrap | 0.5 | 0.75 | 66.67% | High | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Art | Trim (variant 2) Mesh Unwrap | 0.5 | 1 | 50% | High | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Art | Simple Plane Mesh Unwrap | 0.1 | 0.25 | 40% | High | Robbie | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0
Art | Sky Dome Mesh Unwrap | 0.5 | 0.25 | 200% | High | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Art | All Mockup Static Mesh Textures | 4.25 | 0.25 | 1700% | Med | Waylon | 4.25 | 4.25 | 0 | 0 | 0 | 0 | 0 | 0
Art | All Mockup Static Mesh Textures | 0.5 | 0.25 | 200% | Med | Wade-Hahn |  |  | 0 | 0 | 0 | 0 | 0 | 0
Art | Mashu Mesh Skeleton | 1 | 3 | 33.33% | High | Alex | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Art | Mashu Idle | 1.5 | 2 | 75% | Med | Alex | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0
Art | Column diffuse Texture | 1 | 0.25 | n/a | High | Alex | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75
Art | Column normal Texture | 0.7 | 0.75 | 93.33% | High | Alex | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0
Art | Column Base diffuse Texture | 0.5 | 0.5 | n/a | High | Alex | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Art | Column Base normal Texture | 0.25 | 0.75 | 33.33% | High | Alex | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Art | All Mockup Character Meshes | 6 | 12 | 50% | Med | Alex | 6 | 9 | 3 | 0 | 0 | 0 | 0 | 0
Art | All Mockup Character Mesh Textures | 4.25 | 0.25 | 1700% | Med | Waylon | 4.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | All Mockup Particle Textures | 0.75 | 0.25 | 300% | Med | Waylon | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | All Mockup Particle Textures | 0 | 0.25 | 0% | Med | Wade-Hahn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | All Mockup UI/HUD | 1.5 | 0.25 | 600% | Med | Waylon | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Brick Normal | 0.75 | 0.75 | 100% | Low | Alex | days in sprint / effort left 0: 0.75; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Art | Floor Normal | 0.75 | 0.75 | 100% | Low | Alex | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Art | Floor Diffuse | 1 | 1 | 100% | Med | Alex
Art | Rubble Mesh | 0.75 | 0.75 | 100% | Med | Robbie
Art | Rubble Unwrap | 1 | 0.25 | 400% | Med | Robbie
Art | Brick Diffuse | 1 | 2 | 50% | Low | Alex
Art | Mashu Walk Anim | 1.5 | 3 | 50% | High | Alex
Art | Mashu Turn-in-Place Anim | 0.5 | 3 | 16.67% | High | Alex
Art | Parallax/Alpha Map Brick | 0.5 | 0.5 | 100% | Low | Robbie | days in sprint / effort left 7: 0
Level Design
Level Design | Brushwork
Level Design | Create Initial BSP Brushwork | 6 | 5 | 120% | High | Rich | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Create Initial Post-Processing Volume for Shadow Realm | 0 | 0 | 100% | Med | Robbie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Evaluate Initial BSP Brushwork | 0.5 | 0.25 | 200% | High | Rich | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Evaluate Initial Post-Processing Volume for Shadow Realm | 0 | 0 | 100% | Med | Rich | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Materials
Level Design | Import all mockup textures | 3 | 3 | 100% | High | Chris | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Create all mockup materials | 1 | 2 | 50% | Med | Waylon | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Level Design | Place Brick Material Mockup | 0.5 | 0.25 | 200% | Low | Rich | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Level Design | Place Calm Water Material Mockup | 0.5 | 0 | 0% | Low | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Level Design | Place Running Material Mockup | 0.5 | 0 | 0% | Low | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Level Design | Place Floor Material Mockup | 0.5 | 0.25 | 200% | Low | Rich | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Level Design | Import Brick Texture | n/a | 0.25 | n/a | High | Chris | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Level Design | Import Floor Texture | n/a | 0.25 | n/a | High | Chris | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Level Design | General Environmental
Level Design | Generate Navmesh Initial | 0.25 | 0.25 | 100% | High | Rich | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0
Level Design | Create Player Start | 0.25 | 0.25 | 100% | High | Rich | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0
Level Design | Static Meshes
Level Design | Import Static Meshes | 3.25 | 0.25 | 1300% | High | Chris | 3.25 | 3.25 | 3.25 | 0 | 0 | 0 | 0 | 0
Level Design | Mockup Mesh Collisions | 0.25 | 0.25 | 100% | High | Chris | days in sprint / effort left 4: 0; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Level Design | Mockup Particle Systems | 1 | 2 | 50% | Med | Chris | days in sprint / effort left 4: 0; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Level Design | Place Column Static Mesh Mockup in Level | 0.5 | 0.5 | 100% | Med | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Level Design | Place Column Base Static Mesh Mockup in Level | 0.5 | 0.5 | 100% | Med | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Level Design | Place Trim 1 Static Mesh Mockup in Level | 1 | 1 | 100% | Med | Rich | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Level Design | Place Trim 2 Static Mesh Mockup in Level | 1 | 0 | 0% | Med | Rich | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Level Design | Place Rubble Static Mesh Mockup in Level | 1 | 0.25 | 400% | Med | Rich | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Level Design | Place Floor Tile Static Mesh Mockup in Level | 1 | 0 | 0% | Med | Rich | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Level Design | Place Health Urn Static Mesh Mockup in Level | 0.5 | 0.5 | 100% | Med | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Level Design | Place Simple Plane Static Mesh Mockup in Level | 1 | 0.75 | 133.3% | Med | Rich | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Level Design | Place Brazier Static Mesh Mockup in Level | 0.5 | 0.5 | 100% | Med | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Level Design | Place Tree Static Mesh Mockup in Level | 0.25 | 0.25 | 100% | Med | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Level Design | Place Foliage 1 Static Mesh Mockup in Level | 0.5 | 0.25 | 200% | Med | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Level Design | Place Foliage 2 Static Mesh Mockup in Level | 0.5 | 0.5 | 100% | Med | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Level Design | Place God Ray 1 Static Mesh Mockup in Level | 0.25 | 0.25 | 100% | Med | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Level Design | Evaluate Column Static Mesh Mockup in Level | 0.25 | 0.25 | 100% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Level Design | Evaluate Column Base Static Mesh Mockup in Level | 0.25 | 0.25 | 100% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Level Design | Evaluate Trim 1 Static Mesh Mockup in Level | 0.25 | 0 | 0% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Evaluate Trim 2 Static Mesh Mockup in Level | 0.25 | 0 | 0% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Evaluate Rubble Static Mesh Mockup in Level | 0.25 | 0 | 0% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Evaluate Floor Tile Static Mesh Mockup in Level | 0.25 | 0 | 0% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Evaluate Health Urn Static Mesh Mockup in Level | 0.25 | 0 | 0% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Evaluate Simple Plane Static Mesh Mockup in Level | 0.25 | 0 | 0% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Evaluate Brazier Static Mesh Mockup in Level | 0.25 | 0.25 | 100% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Level Design | Evaluate Tree Static Mesh Mockup in Level | 0.25 | 0.25 | 100% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Level Design | Evaluate Foliage 1 Static Mesh Mockup in Level | 0.25 | 0 | 0% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Evaluate Foliage 2 Static Mesh Mockup in Level | 0.25 | 0 | 0% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Evaluate God Ray 1 Static Mesh Mockup in Level | 0.25 | 0.25 | 100% | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Level Design | Evaluate all remaining Static Mesh placement | 2 | 0.5 | 400% | Low | Rich | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
Level Design | Skeletal Meshes
Level Design | Import Player Skeletal Mesh Final into UDK | 0.25 | 0.25 | 100% | High | Chris | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Import Boss Skeletal Mesh Final into UDK | 0.25 | 0.25 | 100% | High | Tony | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Lighting
Level Design | Place Point Lights | 0.5 | 0.25 | 200% | High | Rich | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Place Spot Lights | 0.5 | 0.25 | 200% | High | Rich | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Place Sky Light | 0.25 | 0.25 | 100% | High | Rich | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Scripting
Level Design | Spawn Boss | 2 | 3.5 | 57.14% | High | Waylon | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Level Design | Spawn Health | 0.5 | 0 | n/a | High | Waylon | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Level Design | Spawn Boss Projectile | 3 | 0 | n/a | Med | Waylon | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Level Design | Update Boss for 2nd Stage | 0.5 | 1 | 50% | Med | Waylon | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Level Design | Door Close | 0.5 | 0.5 | 100% | Med | Rich | days in sprint / effort left 5: 0.5; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Level Design | Matinee
Level Design | Prototype matinee cinematic camera movement for Intro | 3 | cut | n/a | High | Wade-Hahn | 3 | 6 | 6 | 9 | 0 | 0 | 0 | 0
Level Design | Employ basic animations using mockup assets for Intro | 3 | cut | n/a | Med | Wade-Hahn | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Level Design | Prototype matinee cinematic camera movement for shift to shadow world | 6 | cut | n/a | High | Wade-Hahn | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
Level Design | Employ basic animations using mockup assets for shift to shadow world | 6 | cut | n/a | Med | Wade-Hahn | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
Level Design | Prototype matinee cinematic camera movement for boss death | 3 | cut | n/a | High | Wade-Hahn | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Level Design | Employ basic animations using mockup assets for boss death | 3 | cut | n/a | Med | Wade-Hahn | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Level Design | Feature Demo | 9 | 9 | 100% | High | Wade-Hahn |  |  | 9 | 6 | 3 | 3 | 0 | 0
Level Design | Tutorials | 6 | 6 | 100% | Med | Wade-Hahn |  | 6 | 3 | 0 | 0 | 0 | 0 | 0
Level Design | Initial Kismet | 3 | 1 | 300% | Med | Wade-Hahn | days in sprint / effort left 4: 3; days in sprint / effort left 5: 3; days in sprint / effort left 6: 3; days in sprint / effort left 7: 0
Level Design | Storyboards | 3 | 2 | 150% | High | Wade-Hahn | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Sound
Sound | Appropriation
Sound | Appropriate Player Stepping on Stone Sound Effect | 0.25 | 0.25 | 100% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Player Stepping in Water Sound Effect | 0.25 | 0.25 | 100% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Player Slashing Sound Effect | 0.25 | 0.25 | 100% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Player Slash Hits Enemy Sound Effect | 0.25 | 0.35 | 71.43% | Low | Chris | 0.25 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Player Slash Hits Urn Sound Effect | 0.25 | 0.15 | 166.7% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Player Slash Hits Stone Sound Effect | 0.25 | 0.15 | 166.7% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Player Takes Damage Sound Effect | 0.25 | 0.15 | 166.7% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Player Death Sound Effect | 0.25 | 0.15 | 166.7% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Boss Stepping on Stone Sound Effect | 0.25 | 0.1 | 250% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Boss Stepping in Water Sound Effect | 0.25 | 0.1 | 250% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Boss Swiping Sound Effect | 0.25 | 0.1 | 250% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Boss Swipe Hits Player Sound Effect | 0.25 | 0.1 | 250% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Boss Swipe Hits Stone Sound Effect | 0.25 | 0.25 | 100% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Boss Wing Flap Sound Effect | 0.25 | 0.1 | 250% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Boss Roar Sound Effect | 0.25 | 0.25 | 100% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Boss Banish Sound Effect | 0.25 | 0.2 | 125% | Low | Chris | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Boss Takes Damage Sound Effect | 0.25 | 0.1 | 250% | Low | Chris | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Boss Death Sound Effect | 0.25 | 0.1 | 250% | Low | Chris | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Ambient Water Rippling Sound Effect | 0.25 | 0.2 | 125% | Low | Chris | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Ambient Water Rushing Sound Effect | 0.25 | 0.1 | 250% | Low | Chris | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Shadow World Transition Sound Effect | 0.25 | 0.1 | 250% | Low | Chris | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Shadow World Ambient Voices Sound Effects | 0.25 | 0.25 | 100% | Low | Chris | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Import
Sound | Import sounds | 0.25 | 0.25 | 100% | Low | Chris | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0
Production
Production | Update Production Scrum Boards | 2 | 3 | 66.67% | High | Chris |  | 2 | 0 | 0 | 0 | 0 | 0 | 0
Production | Create Weekly DVD Backup | 0.5 | 0.5 | 100% | High | Chris | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Production | Compile Backlog Actuals | 2 | 0.5 | 400% | High | Chris | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Production | Organize Packages | 1 | 1 | 100% | High | Waylon | days in sprint / effort left 4: 0; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Production | Reorganize Packages | 1 | 2 | 50% | High | Chris | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Production | Reorganize Packages | 1 | 1.5 | 66.67% | High | Rich | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Production | Fix Asset Pipeline and Create New Chart for Team | 1 | 1 | 100% | High | Chris | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Production | Art team meeting, Tutorial Session 1 | 0.75 | 1 | 75% | Med | Alex | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0
Production | Art team meeting, Tutorial Session 1 | 0.75 | 1 | 75% | Med | Robbie | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0
Production | Game Design Updates | 1 | 2.5 | 40% | Med | Robbie | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Production | Update Controls | 0.25 | 0.25 | 100% | Med | Robbie | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0
Production | Update LDD | 1 | cut | n/a | Med | Rich | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Update TDD | 1 | cut | n/a | Med | Loren | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Update ASG | 1 | cut | n/a | Med | Alex | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Update Product Backlog | 1 | 1 | 100% | Med | Chris | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Production | Update ADP | 1 | 1 | 100% | Med | Chris | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 1 | 1 | 1 | 100% | Low | Chris | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 2 | 1 | 1.5 | 66.67% | Low | Chris | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 3 | 1 | 1 | 100% | Low | Chris | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 4 | 1 | 1.5 | 66.67% | Low | Chris | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 5 | 1 | 1 | 100% | Low | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Calculate Remaining Effort - Day 6 | 1 | 0.5 | 200% | Low | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Update Asset Database | 1 | cut | n/a | Low | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Art Team Meeting, Review and Correct | 2 | 1 | 200% | Med | Alex | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Production | Art Team Meeting, Review and Correct | 2 | 1 | 200% | Med | Robbie | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Production | PPT for Sprint Review | 1 | 0.5 | 200% | Med | Chris | days in sprint / effort left 6: 1; days in sprint / effort left 7: 0
Production | Kleenex Test | 0.5 | cut | n/a | High | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Kleenex Test | 0.5 | cut | n/a | Med | Wade-Hahn | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Kleenex Test | 0.5 | cut | n/a | Low | Waylon | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Kleenex Test | 0.5 | cut | n/a | High | Ben | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Kleenex Test | 0.5 | cut | n/a | Low | Tony | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | Med | Chris | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | High | Alex | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | Med | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | High | Loren | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 1 | 1.5 | 66.67% | High | Robbie | days in sprint / effort left 6: 1; days in sprint / effort left 7: 0
Production | Sprint Review | 1 | 1.5 | 66.67% | High | Wade-Hahn | days in sprint / effort left 6: 1; days in sprint / effort left 7: 0
Production | Sprint Review | 1 | 1.5 | 66.67% | High | Waylon | days in sprint / effort left 6: 1; days in sprint / effort left 7: 0
Production | Sprint Review | 1 | 1.5 | 66.67% | High | Ben | days in sprint / effort left 6: 1; days in sprint / effort left 7: 0
Production | Sprint Review | 1 | 1.5 | 66.67% | High | Tony | days in sprint / effort left 6: 1; days in sprint / effort left 7: 0
Production | Sprint Retrospective/Planning Meeting | 1 | 1.5 | 66.67% | High | Loren | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 1.5 | 66.67% | High | Tony | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 1.5 | 66.67% | High | Ben | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 1.5 | 66.67% | High | Alex | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 1.5 | 66.67% | High | Rich | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 1.5 | 66.67% | High | Robbie | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 1.5 | 66.67% | High | Waylon | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 1.5 | 66.67% | High | Wade-Hahn | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 1.5 | 66.67% | High | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
http://agilesoftwaredevelopment.com/scrum/simple-sprint-backlog
Note on B1: sprint goal
Note on B225: See for reference and comments. Feel free to remove the link, though it would be very kind of you to leave it somewhere on the sheet

## Interim MS2
Sprint 2. Interim MS2
Not Finished/Moved to Next Milestone
days in sprint / effort left
| Tasks | Estimate | Actual | Accuracy | Priority | Assigned To: | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
[7 empty] | 270.2 | 248.7 | 215.2 | 200.7 | 175.61 | 141.45 | 103.45 | 96.7 | 37.95
Programming
Programming | Player character using final model assets | 3 | 4 | 75% | High | Tony | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 0
Programming | Player character can dodge | 6 | 1 | 600% | High | Tony | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
Programming | Shedu has ranged attack | 6 | 2.5 | 240% | High | Ben | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
Programming | HUD utilizes art assets for appearance | 3 | 3 | 100% | High | Loren | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
Programming | HUD queries game for presence of boss | 1 | cut | N/A | High | Loren | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Programming | Game supports single level and matinee cinematics | 5 | N/A | N/A | High | Loren | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Events may be triggered to advance player to the next level | 3 | cut | N/A | High | Loren | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
Programming | Create alpha installer | 1 | 1 | 100% | High | Loren | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Programming | HUD informs player of lock on | 3 | 1 | 300% | Med | Loren | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Main menu in place | 3 | 3 | 100% | Med | Loren | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Pause menu in place | 1 | 1 | 100% | Low | Loren | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Death screen in place | 3 | 1 | 300% | Low | Loren | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Player character can lock on to nearest enemy | 6 | 3 | 200% | Med | Tony | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Boss has orb projectile | 6 | 1 | 600% | High | Loren | 6 | 6 | 6 | 6 | 3 | 3 | 1 | 1 | 0
Programming | Boss has fly state | 3 | 2.5 | 120% | High | Ben | 3 | 3 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0
Programming | Shadow motes | 4 | 1 | 400% | Med | Loren | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Moon orbs with ray to boss | 5 | 8 | 62.5% | High | Loren | 5 | 5 | 5 | 5 | 2 | 2 | 1 | 1 | 0
Programming | Shedu character performing single melee attack | 1 | 2 | 50% | High | Ben | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Programming | Game supports a level ending event resulting in a level reset | 2 | 1 | 200% | High | Loren | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Shedu State and Decision System | 3 | 7.5 | 40% | High | Ben | 3 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
Programming | PC can dodge | 3 | 3 | 100% | High | Tony | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Shedu charge attack | 2.5 | 5 | 50% | High | Ben | 2.5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Programming | Shedu Strafing | 2 | 2 | 100% | High | Ben | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Load next Level | 3 | 0.5 | 600% | High | Loren | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Hero can juke & info is available | 3 | 3 | 100% | High | Tony |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Programming | Shedu Sound Integration | 3 | 2 | 150% | High | Ben | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Programming | Boss Pathing | 2 | 2 | 100% | High | Ben | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Programming | Health Urn | 1 | 1 | 100% | High | Loren | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Programming | Fix Shedu Sounds | 1 | 1 | 100% | High | Ben | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Programming | Hero Sound Integration | 1 | 1 | 100% | High | Tony | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Programming | Fix Bugs | 1 | 2 | 50% | High | Ben | days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Programming | Integrate game for Sprint Review | 5 | 10 | 50% | High | Loren | days in sprint / effort left 8: 0
Programming | Post-Process | 6 | 2 | 300% | Med | Loren | days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Art
Art | Brick Solo Mesh | 0.25 | 0 | N/A | High | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Art | Brick Solo Mesh Unwrap | 0.25 | 0 | N/A | High | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Art | Brick Solo diffuse Texture | 0.5 | 0 | N/A | High | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Art | Brick Solo normal Texture | 0.25 | 0 | N/A | High | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Art | Rubble Mesh | 1 | 1 | 100% | High | Robbie | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Art | Rubble Mesh Unwrap | 1 | 0.5 | 200% | High | Robbie | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Art | Rubble diffuse Texture | 1 | 1 | 100% | High | Robbie | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Art | Rubble normal Texture | 1 | 1 | 100% | High | Robbie | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Art | Water Drips Mesh | 0.5 | 0 | N/A | Med | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Art | Water Drips Mesh Unwrap | 0.5 | 0 | N/A | Med | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Art | Foliage Mesh | 2 | 1 | 200% | Med | Robbie | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Art | Foliage Mesh Unwrap | 2 | 2 | 100% | Med | Robbie | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0 | 0
Art | Foliage diffuse Texture | 1 | 1 | 100% | Med | Robbie | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Art | Trim (variant 1) diffuse Texture | 0.25 | 1 | 25% | High | Robbie | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Trim (variant 1) normal Texture | 0.25 | 0.75 | 33.33% | High | Robbie | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Trim (variant 2) diffuse Texture | 0.25 | 0.5 | 50% | High | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Trim (variant 2) normal Texture | 0.25 | 0.5 | 50% | High | Robbie | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Water Drip Texture normal 1 Texture | 0.25 | 0 | N/A | Med | Robbe | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Art | Water Drip Texture normal 2 Texture | 0.25 | 0 | N/A | Med | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Art | Water Drip Texture alpha Texture | 0.25 | 0 | N/A | Med | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Art | Sky diffuse Texture | 3 | 1.5 | 200% | High | Alex | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
Art | Mashu Mesh | 5 | 5.5 | 90.91% | High | Alex | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Mashu Mesh Unwrap | 3 | 7.5 | 40% | High | Alex | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Art | Mashu Reweight Skeleton | 6 | 8 | 75% | High | Alex |  |  | 6 | 4 | 0 | 0 | 0 | 0 | 0
Art | Shedu Mesh | 5 | 2 | 250% | High | Alex | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 18.44
Art | Shedu Mesh Unwrap | 3 | 7.25 | 41.38% | High | Alex | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
Art | Shedu Projectile Mesh | 0.2 | 0 | N/A | High | Alex | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
Art | Shedu Projectile Mesh Unwrap | 0.25 | 0 | N/A | High | Alex | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Art | Shedu Mesh Skeleton | 2 | 4 | 50% | High | Alex | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Art | Mashu Running | 3 | 0 | N/A | High | Alex | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Art | Mashu Attack Combo 1 | 3 | 1.5 | 200% | High | Alex | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
Art | Mashu Dodge (R. side) | 3 | 2 | 150% | High | Alex | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Art | Mashu Dodge (L. side) | 0.5 | 0.5 | 100% | High | Alex | days in sprint / effort left 5: 0.5; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Art | Mashu Dodge (back) | 3 | 0 | N/A | High | Alex | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Art | Mashu Juke | 4 | 0 | N/A | High | Alex | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Art | Shedu Running | 3 | 2 | 150% | High | Alex | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
Art | Shedu Charges | 3 | 2 | 150% | High | Alex | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
Art | Shedu Swipe | 2 | 1 | 200% | High | Alex | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Art | Shedu Idle | 1.5 | 1 | 150% | Med | Alex | days in sprint / effort left 5: 1.5; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Art | Floating Idle Anim | 3 | 1 | 300% | High | Alex | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
Art | Shedu Side Step | 3 | 0 | N/A | Med | Alex | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Art | Mashu diffuse Texture | 3 | 0 | N/A | High | Alex | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Art | Shedu diffuse Texture | 3 | 0 | N/A | High | Alex | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Art | Orb Mesh | 0.25 | 0.25 | 100% | High | Robbie | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Orb Mesh Unwrap | 0.25 | 0.25 | 100% | low | Robbie | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Orb Specular Texture | 1 | 0 | N/A | Low | Robbie | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Art | Orb Material | 0.5 | 0.5 | 100% | High | Robbie | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Column Diffuse | 0.5 | 0.5 | 100% | High | Alex | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Column Base Diffuse | 0.5 | 1.5 | 33.33% | High | Alex | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Urn Unwrap | 0.75 | 0.75 | 100% | High | Robbie |  |  | 0.75 | 0 | 0 | 0 | 0 | 0 | 0
Art | Urn Diffuse | 0.66 | 1 | 66% | High | Robbie | days in sprint / effort left 4: 0.66; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Art | Urn Mesh | 0.75 | 0.75 | 100% | High | Robbie |  |  | 0.75 | 0 | 0 | 0 | 0 | 0 | 0
Art | Urn Normal | 0.33 | 3 | 11% | Med | Robbie | days in sprint / effort left 4: 3; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design
Level Design | Brushwork
Level Design | Finalize BSP Brushwork | 6 | 4 | 150% | High | Rich | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Finalize Post-Processing | 0.5 | 0.5 | 100% | Med | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Level Design | General Environment
Level Design | Generate Navmesh | 0.25 | 0.25 | 100% | High | Rich | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | BSP Textures
Level Design | Import Final BSP Textures | 0.25 | cut | N/A | High | Chris | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0
Level Design | Create Floor Material Final | 1 | 0 | N/A | High | Waylon | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Level Design | Create Wall Material Final | 1 | 0 | N/A | High | Waylon | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Level Design | Place Floor Material Final | 0.5 | 0 | N/A | High | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Level Design | Place Wall Material Final | 0.5 | 0 | N/A | High | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Level Design | Static Meshes
Level Design | Import Gameplay Static Mesh Finals into UDK | 0.25 | 0.25 | 100% | High | Waylon | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0
Level Design | Create Column Static Mesh Final Material | 1 | 1 | 100% | High | Waylon | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Create Column Base Static Mesh Final Material | 1 | 1 | 100% | High | Waylon | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Create Health Urn Static Mesh Final Material | 1 | 1 | 100% | High | Waylon | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Level Design | Create Simple Plane Static Mesh Final Material | 1 | 0 | N/A | High | Waylon | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Level Design | Place Column Static Mesh Final | 0.5 | 0.25 | 200% | High | Rich | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Place Column Base Static Mesh Final | 1 | 0.25 | 400% | High | Rich | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Place Health Urn Static Mesh Final | 0.5 | 0.25 | 200% | High | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Level Design | Place Simple Plane Static Mesh Final | 1 | 0 | N/A | High | Rich | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Level Design | Trim 1 Static + Material | 0.25 | 0.25 | 100% | Med | Waylon |  |  |  | 0.25 | 0 | 0 | 0 | 0 | 0
Level Design | Trim 2 Static + Material | 0.25 | 0.5 | 50% | Med | Waylon |  |  |  | 0.25 | 0 | 0 | 0 | 0 | 0
Level Design | Place Roof Trim | 1 | 1 | 100% | Med | Waylon | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Place Upper Level Trim | 3 | 3 | 100% | Med | Waylon | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Skeletal Meshes
Level Design | Create Player Skeletal Mesh Final Material | 2 | 0 | N/A | High | Waylon | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Level Design | Create Boss Skeletal Mesh Final Material | 2 | 0 | N/A | High | Waylon | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Level Design | Import Player Bones into UDK | 0.25 | cut | N/A | High | Chris | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Import Boss Bones into UDK | 0.25 | cut | N/A | High | Chris | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Import Player Animation Sequences into UDK | 0.25 | cut | N/A | High | Chris | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Import Boss Animation Sequences into UDK | 0.25 | cut | N/A | High | Chris | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Particle Effects
Level Design | Brazier Particle | 6 | 4 | 150% | High | Chris | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Miasma Particle Effect | 4 | 2.5 | 160% | High | Chris |  |  |  | 4 | 4 | 1 | 0 | 0 | 0
Level Design | Create Health Urn Splash Particle System | 3 | 3.5 | 85.71% | High | Chris | 3 | 3 | 3 | 4 | 4 | 0 | 0 | 0 | 0
Level Design | Dust - Mashu Step | 2 | 1.5 | 133.3% | Low | Chris | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Dust - Shedu Step | 2 | 0.75 | 266.7% | Low | Chris |  | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Level Design | Dust - Shedu Charge | 1 | 0.25 | 400% | Med | Chris | days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Dust - Shedu Wing Flap | 1 | 0.5 | 200% | Med | Chris | days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Evaluate Health Urn Splash Particle Effect | 0.25 | cut | N/A | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Level Design | Evaluate Brazier Fire Particle Effect | 0.25 | cut | N/A | Low | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Level Design | Lighting
Level Design | Place Point Lights | 0.5 | 0.25 | 200% | High | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Level Design | Place Spot Lights | 0.25 | 0.25 | 100% | High | Rich | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Place Sky Light | 0.25 | 0.25 | 100% | High | Rich | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Change Point Light Properties to Representational Quality | 0.5 | 0.5 | 100% | High | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Level Design | Change Spot Light Properties to Representational Quality | 0.5 | 1 | 50% | High | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Level Design | Change Sky Light Properties to Representational Quality | 0.25 | 0.25 | 100% | High | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0
Level Design | Change Lightmass Settings to Representational Quality | 0.5 | 1 | 50% | Med | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Level Design | Scripting
Level Design | Trigger "Brazier" sequence | 1 | 3 | 33.33% | Med | Waylon | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Level Design | Spawn Soul Orbs | 1 | 1 | 100% | High | Waylon | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Level Design | Spawn Shadow Hazards | 1 | 0 | N/A | High | Waylon | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Level Design | Trigger Particle Effects | 1 | 1 | 100% | Low | Waylon | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Level Design | Scripting Phase 1 to 2 Transitions | 1 | 1.5 | 66.67% | High | Waylon | days in sprint / effort left 8: 0
Level Design | Scripting Phase 2 to 3 Transitions | 1 | 1.5 | 66.67% | High | Waylon | days in sprint / effort left 8: 0
Level Design | Matinee
Level Design | Shippable quality matinee cinematic camera movement for Intro | 3 | 6 | 50% | High | Wade-Hahn | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Employ basic animations using mockup assets for Intro | 3 | 3 | 100% | Med | Wade-Hahn | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Prototype matinee cinematic camera movement for shift to second floor | 6 | 6 | 100% | High | Wade-Hahn | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0
Level Design | Employ basic animations using mockup assets for shift to second floor | 6 | 3 | N/A | Med | Wade-Hahn | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3
Level Design | Transition to Phase 3 Battle Mockup | 3 | 3 | 100% | Med | Wade-Hahn | days in sprint / effort left 4: 3; days in sprint / effort left 5: 3; days in sprint / effort left 6: 3; days in sprint / effort left 7: 3; days in sprint / effort left 8: 0
Level Design | Prototype matinee cinematic camera movement for boss death | 3 | cut | N/A | High | Wade-Hahn | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Level Design | Employ basic animations using mockup assets for boss death | 3 | cut | N/A | Med | Wade-Hahn | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Level Design | Scripting matinee Transitions between all 3 phases | 2 | 2 | 100% | Med | Wade-Hahn | days in sprint / effort left 8: 0
Sound
Sound | Appropriation
Sound | Appropriate Title Music | 1 | 1 | 100% | Med | Rich | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Sound | Appropriate Boss Music | 1 | 1 | 100% | High | Rich | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Sound | Importing
Sound | Import Boss & Title Music | 0.25 | 0.75 | 33.33% | High | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Appropriate and Import
Sound | Fire | 0.5 | 0.5 | 100% | High | Waylon | days in sprint / effort left 4: 0.5; days in sprint / effort left 5: 0.5; days in sprint / effort left 6: 0.5; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Sound | Soul Orb Shot | 0.25 | 0.25 | 100% | High | Chris | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Sound | Soul Orb-Soul Orb Collision | 0.25 | 0.25 | 100% | High | Chris | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Sound | Shedu Soul Orb Charge-Up | 0.25 | 0.25 | 100% | High | Chris | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Sound | Soul Orb Beams | 0.25 | 0.75 | 33.33% | High | Chris | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Sound | NEW Shedu Step | 0.25 | 0.25 | 100% | High | Chris | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Sound | Placing
Sound | Place Ambient Sound Effects | 0.5 | 0.25 | 200% | Low | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Sound | Settings
Sound | Finalize Ambient Music Settings | 0.5 | 0 | N/A | Low | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Sound | Finalize Boss & Title Music Settings | 0.5 | 0.25 | 200% | Low | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Production
Production | Art Lead/LD Lead meeting, Tutorial Session (Implementing Assets) | 0.75 | 1 | 75% | Med | Alex | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0
Production | Art Lead/LD Lead meeting, Tutorial Session (Implementing Assets) | 0.75 | 1 | 75% | Med | Rich | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0
Production | Art Lead/LD Lead meeting (materials review and approval) | 0.75 | cut | N/A | Med | Alex | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0
Production | Art Lead/LD Lead meeting (materials review and approval) | 0.75 | cut | N/A | Med | Rich | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0
Production | Art Lead/LD Lead meeting (lighting review and approval) | 0.75 | cut | N/A | Med | Alex | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0
Production | Art Lead/LD Lead meeting (lighting review and approval) | 0.75 | cut | N/A | Med | Rich | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0
Production | Art Lead/LD Lead/Tech Lead meeting (Bone Systems and Animation) | 2 | 0.5 | 400% | High | Alex | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Production | Art Lead/LD Lead/Tech Lead meeting (Bone Systems and Animation) | 2 | cut | N/A | High | Rich | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Production | Art Lead/LD Lead/Tech Lead meeting (Bone Systems and Animation) | 2 | 0.5 | 400% | High | Tony | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Production | Art Tutorials (Particles, Curve Editor) | 1 | 1 | 100% | Low | Robbie |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Production | Compile V.Slice Actuals | 1 | 2 | 50% | Med | Chris | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Revise Scrum Board & Backlog | 2 | 1 | 200% | Med | Chris | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Create Weekly DVD Backup | 0.5 | 0.25 | 200% | High | Loren | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Production | Create Weekly DVD Backup | 0.5 | 0.25 | 200% | High | Loren | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Production | Game Progression Breakdown | 1 | 1 | 100% | High | Robbie | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Update GDD | 2 | cut | N/A | Med | Robbie | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Production | Update TDD | 1 | cut | N/A | Med | Loren | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Update ASG | 2 | cut | N/A | Med | Alex | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Production | Update LDD | 2 | cut | N/A | Med | Rich | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Production | Calculate Remaining Effort - Day 1 | 1 | 0.75 | 133.3% | Low | Chris | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 2 | 1 | 0.5 | 200% | Low | Chris | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 3 | 1 | 0.5 | 200% | Low | Chris | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 4 | 1 | 0.5 | 200% | Low | Chris | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 5 | 1 | 0.5 | 200% | Low | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 6 | 1 | 1 | 100% | Low | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Production | Calculate Remaining Effort - Day 7 | 1 | 0.75 | 133.3% | Low | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Calculate Remaining Effort - Day 8 | 1 | 0.25 | 400% | Low | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
Production | Update Sprint Backlogs (alpha, Beta, RTM) | 1 | 1.5 | 66.67% | High | Chris |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Review Prod. Baclog with Prof. Stringer | 0.5 | 0.5 | 100% | Med | Chris |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Update Product Backlog | 2 | cut | N/A | Med | Chris | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Production | Update Asset Database | 1 | cut | N/A | Low | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Update ADP | 1 | 0.5 | 200% | Med | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Art Team Meeting, Review and Correct | 2 | 2 | 100% | Med | Alex | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Production | Art Team Meeting, Review and Correct | 2 | 2 | 100% | Med | Robbie | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | Low | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | High | Wade-Hahn | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | Low | Waylon | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | High | Ben | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | High | Tony | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | High | Chris | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | Low | Alex | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | Med | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 1.5 | 33.33% | Low | Loren | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Loren | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Tony | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Ben | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Alex | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Rich | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Robbie | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Waylon | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Wade-Hahn | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Level Design Milestone Definitions Meeting | 1 | 1 | 100% | High | Chris | days in sprint / effort left 8: 0
Production | Level Design Milestone Definitions Meeting | 1 | 1 | 100% | High | Robbie | days in sprint / effort left 8: 0
Production | Level Design Milestone Definitions Meeting | 1 | 1 | 100% | High | Rich | days in sprint / effort left 8: 0
Production | Level Design Milestone Definitions Meeting | 1 | 1 | 100% | High | Wade-Hahn | days in sprint / effort left 8: 0
Production | Level Design Milestone Definitions Meeting | 1 | 1 | 100% | High | Waylon | days in sprint / effort left 8: 0
http://agilesoftwaredevelopment.com/scrum/simple-sprint-backlog
Note on B1: sprint goal
Note on B247: See for reference and comments. Feel free to remove the link, though it would be very kind of you to leave it somewhere on the sheet

## First Playable
Sprint 3. First Playable
Not Finished/Moved to Next Milestone
days in sprint / effort left
| Tasks | Estimate | Actual | Accuracy | Priority | Assigned To: | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
[7 empty] | 179.3 | 149.55 | 135.3 | 123.3 | 116.25 | 74 | 71 | 52.5 | 23.25
Programming
Programming | Boss using final anim | 3.5 | 4 | 87.5% | High | Ben | 3.5 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Boss using final assets | 1 | 1 | 100% | High | Ben | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Boss Polish | 1 | 2 | 50% | High | Ben | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Hero flies on Hit | 2 | 0.5 | 400% | High | Ben | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Create beta installer | 1 | 1 | 100% | High | Loren | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Programming | Player control polish | 1 | 7 | 14.29% | Med | Tony | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 0 | 0
Programming | New HUD graphics | 1.5 | 0 | n/a | High | Loren | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Programming | Foot steps | 1 | 1 | 100% | High | Tony | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programming | Boss orb projectile | 1 | 5 | 20% | High | Tony | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Programming | Moon orb work | 1.5 | 1.5 | 100% | High | Loren | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0
Programming | Miasma 2.0 | 2 | 4.5 | 44.44% | High | Loren | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
Programming | Final main menu | 2 | 0 | n/a | High | Loren | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Programming | Integrate sidestep animations in strafe behavior | 1 | 1 | 100% | High | Ben | days in sprint / effort left 4: 0; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Programming | Flinch Damage System | 3 | 2 | 150% | High | Ben | days in sprint / effort left 4: 0; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Art
Art | Brick Solo Mesh | 0.25 | 0.25 | 100% | High | Robbie | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Brick Solo Mesh Unwrap | 0.25 | 0.25 | 100% | High | Robbie | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Brick Solo diffuse Texture | 0.5 | 0.5 | 100% | High | Robbie | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Brick Solo normal Texture | 0.25 | 0.25 | 100% | High | Robbie | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Speedtree Model (Mesh, textures, etc) | 5 | 3 | 166.7% | High | Alex | days in sprint / effort left 4: 5; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Art | Tree Mesh | 5 | n/a | n/a | High | Alex | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0
Art | Tree Mesh Unwrap | 3 | n/a | n/a | High | Alex | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Art | Tree diffuse Texture | 1.5 | n/a | n/a | High | Alex | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0
Art | Tree normal Texture | 1.5 | n/a | n/a | High | Alex | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0
Art | Tree specular Texture | 0.5 | n/a | n/a | High | Alex | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Art | Tree emissive Texture | 0.25 | n/a | n/a | High | Alex | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Tree alpha Texture | 0.5 | n/a | n/a | High | Alex | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Art | Brazier Mesh | 0.75 | 0.75 | 100% | High | Robbie | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Brazier Normal | 0.25 | 0.5 | 50% | High | Robbie | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Brazier Diffuse | 0.5 | 0.75 | 66.67% | High | Robbie | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Broken Column Mesh | 0.5 | 0.5 | 100% | High | Robbie | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Broken Column Unwrap | 1 | 1 | 100% | High | Robbie | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Broken Column Diffuse | 0.5 | 0.5 | 100% | High | Robbie | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Broken Column Normal | 0.5 | 0.5 | 100% | High | Robbie | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | God Ray (variant 1) Mesh | 0.5 | 0.5 | 100% | Low | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Art | God Ray (variant 1) Mesh Unwrap | 0.5 | 0.25 | 200% | Low | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Art | God Ray emissive Texture | 0.25 | 0.25 | 100% | Low | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0
Art | God Ray alpha 1-4 Texture | 0.3 | 1.5 | 20% | Low | Robbie | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0
Art | Foliage normal Texture | 1 | cut | n/a | Med | Robbie | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Art | Foliage specular Texture | 0.5 | cut | n/a | Med | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Art | Brick Solo unwrap | 0.5 | 0.5 | 100% | Med | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Art | Brick Solo normal | 0.25 | 0.25 | 100% | Med | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0
Art | Urn emissive Texture | 0.5 | cut | n/a | Med | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Art | Mashu Diffuse | 3 | 4 | 75% | High | Alex | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Art | Mashu specular Texture | 0.75 | 1 | 75% | High | Alex | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0 | 0 | 0
Art | Mashu normal Texture | 2 | 10 | 20% | High | Alex | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Art | Shedu specular Texture | 0.5 | 0 | n/a | High | Alex | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Art | Shedu normal Texture | 2 | 4 | 50% | High | Alex | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
Art | Shedu emissive Texture | 1 | 0 | n/a | High | Alex | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Art | Shedu alpha Texture | 0.75 | 0 | n/a | High | Alex | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75
Art | Shedu Side Step | 3 | 1 | 300% | Med | Alex | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Mashu Run | 1.5 | 2.5 | 60% | High | Alex | 1.5 | 1.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Art | Mashu Dodge (back) | 3 | 2.25 | 133.3% | High | Alex | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Mashu Right Juke | 1 | 0.25 | 400% | High | Alex | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Mashu Left Juke | 1 | 0.25 | 400% | High | Alex | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Mashu Takes Damage | 1.5 | 0.75 | 200% | Med | Alex | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Shedu Takes Damage | 1.5 | 0.75 | 200% | Med | Alex | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Art | Frieze Relief | 1.5 | 1.5 | 100% | Med | Robbie | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Art | Export/Import HUD assets created in preproduction | 0.5 | 0.5 | 100% | High | Robbie | days in sprint / effort left 4: 0.5; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Art | Game Logo | 2 | 2 | 100% | High | Alex | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Art | Mashu Health | 0.25 | n/a | n/a | Med | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Mashu Endurance | 0.25 | n/a | n/a | Low | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Lock-On-Icon | 0.25 | n/a | n/a | Low | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Mashu Healing | 0.25 | n/a | n/a | Med | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Shedu Health Bar | 0.25 | n/a | n/a | Med | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Team Logo Screen | 0.25 | n/a | n/a | Low | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Game Logo Screen | 0.25 | n/a | n/a | Low | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Start Menu | 0.25 | n/a | n/a | Low | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Quit Menu | 0.25 | n/a | n/a | Low | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Death Menu | 0.25 | n/a | n/a | Low | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Start Menu buttons | 0.25 | n/a | n/a | Low | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Quit Menu buttons | 0.25 | n/a | n/a | Low | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Art | Death Menu buttons | 0.25 | n/a | n/a | Low | Robbie | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0
Level Design
Level Design | Brushwork & Volumes
Level Design | BSP Brushwork | 2 | cut | n/a | High | Rich | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Level Design | Post-Proccessing at ASG Quality | 0.5 | 0.5 | 100% | Med | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Level Design | Fix Unlit Walls | 1 | 0.25 | 400% | High | Waylon | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | General Environmental
Level Design | Navmesh Generate | 0.25 | 0.25 | 100% | High | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Decorate Level | 2 | 3 | 66.67% | Med | Rich | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Clean Up Collisions | 2 | 4.5 | 44.44% | High | Waylon |  |  |  | 2 | 2 | 2 | 2 | 0 | 0
Level Design | Static Meshes
Level Design | Trim 1 Static Mesh Final Material | 1 | cut | n/a | High | Waylon | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Trim 2 Static Mesh Final Material | 1 | cut | n/a | High | Waylon | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Rubble Static Mesh Final Material | 1 | 0.25 | 400% | High | Waylon | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Brazier Static Mesh Final Material | 1 | 0.5 | 200% | High | Waylon | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Tree Static Mesh Final Material | 1 | 0.5 | 200% | High | Rich | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Level Design | Foliage Static Mesh Final Material | 1 | 0.25 | 400% | High | Waylon | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | God Ray Static Mesh Final Material | 1 | 1 | 100% | High | Robbie | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Level Design | Import Column Base Broken (1-5) | 1 | 0.5 | 200% | Med | Waylon |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Place Trim 1 Static Mesh Final | 1 | 1.25 | 80% | High | Rich | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Place Trim 2 Static Mesh Final | 1 | 0.5 | 200% | High | Rich | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Place Rubble Static Mesh Final | 0.5 | 0.25 | 200% | High | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Level Design | Place Tree Static Mesh Final | 0.25 | 0.5 | 50% | High | Rich | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Place Foliage Static Mesh Final | 1 | 1 | 100% | High | Rich | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Place God Ray Static Mesh Final | 0.5 | 1 | 50% | High | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Level Design | Place Miasmas | 0.5 | 0.5 | 100% | High | Rich |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Re-Place Miasmas | 1.5 | 1.5 | 100% | Med | Rich | days in sprint / effort left 4: 0; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Add Collision to Door Mesh | 0.5 | 0.5 | 100% | High | Waylon | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Place Friezes | 1 | 1 | 100% | Med | Rich | days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Skeletal Meshes
Level Design | Import Mashu Textures and Create Material | 0.25 | 0.25 | 100% | High | Waylon | days in sprint / effort left 4: 0.25; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Particle System
Level Design | Fix Dust Texture Color | 0.5 | 0.5 | 100% | Med | Chris | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Optimize Miasma Particle | 0.5 | 1 | 50% | High | Chris |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Create Orb Smash Particle System | 3 | 0.25 | 1200% | High | Chris | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Level Design | Create Orb Beam Particle System | 3 | 6.5 | 46.15% | High | Chris | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
Level Design | Create Orb Trail Particle System | 2 | 1 | 200% | High | Chris | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Create Shedu Hit (Feathers) Particle System | 3 | cut | n/a | High | Chris | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
Level Design | Create Urn Smash Particle System | 3 | 2.5 | 120% | High | Chris | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Level Design | Create Ambient Dust Particle System | 3 | 2 | 150% | High | Chris | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
Level Design | Fix LOD on Orb Beam | 0.25 | 0.25 | 100% | Med | Chris | days in sprint / effort left 4: 0.25; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Attach Dust Particles to character animations | 2 | 2.5 | 80% | Med | Chris | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Lighting
Level Design | Point Light Properties at ASG Quality | 0.5 | 0 | n/a | High | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Level Design | Spot Light Properties at ASG Quality | 0.5 | 0 | n/a | High | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Level Design | Sky Light Properties at ASG Quality | 0.5 | 0 | n/a | High | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Level Design | Lightmass Settings at ASG Quality | 1 | 0 | n/a | High | Rich | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Level Design | Matinee
Level Design | Employ basic animations using mockup assets for shift to second floor | 3 | 3 | 100% | Med | Wade-Hahn | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Camera work Polish/edit, Intro | 3 | 3 | 100% | Med | Wade-Hahn | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
Level Design | Animations, Intro | 3 | 3 | 100% | Med | Wade-Hahn | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Level Design | Camera work, Boss death | 3 | cut | n/a | Med | Wade-Hahn | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Level Design | Animations, Boss Death | 3 | cut | n/a | Med | Wade-Hahn | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Level Design | Camera work, Transition to Shadow mode | 6 | 6 | 100% | High | Wade-Hahn | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
Level Design | Animations, Transition to Shadow World | 3 | 1 | n/a | Med | Wade-Hahn | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2
Level Design | Camera work, Transition from Shadow mode | 6 | 0 | n/a | High | Wade-Hahn | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Level Design | Animations, Transition from Shadow mode | 3 | 0 | n/a | Med | Wade-Hahn | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Level Design | Fix Anim Track Bug | 3 | 3 | 100% | High | Wade-Hahn | days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Scripting
Level Design | Separate Matinee and Scripting Levels (Level Streaming) | 2 | 5.25 | 38.1% | High | Waylon | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Fix teleport bug | 0.5 | 1 | 50% | High | Waylon |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Spawn Miasmas | 1 | 2 | 50% | High | Waylon | days in sprint / effort left 4: 1; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Fix blocked Projectile Bug | 1 | 1 | 100% | High | Waylon | days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Level Design | Scripting Post-Process around Miasma Particles | 1 | 1 | 100% | Med | Waylon | days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Sound
Sound | Title Music | 1 | 2 | 50% | High | Rich | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound | Death Music | 1 | 2 | n/a | High | Rich | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Sound | Boss Death Music | 1 | 0 | n/a | High | Rich | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Production
Production | Art team meeting, Tutorial Session 2 | 0.75 | cut | n/a | Med | Alex | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0
Production | Art team meeting, Tutorial Session 2 | 0.75 | cut | n/a | Med | Robbie | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0
Production | Level Streaming Tutorial | 0.5 | 0.5 | 100% | High | Rich | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Curve Editor Tutorial | 0.3 | 0.3 | 100% | Med | Robbie | days in sprint / effort left 4: 0; days in sprint / effort left 5: 0; days in sprint / effort left 6: 0; days in sprint / effort left 7: 0; days in sprint / effort left 8: 0
Production | LD Meeting - Improving Workflow (Level Streaming) | 0.25 | 0.25 | 100% | High | Rich | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | LD Meeting - Improving Workflow (Level Streaming) | 0.25 | 0.25 | 100% | High | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | LD Meeting - Improving Workflow (Level Streaming) | 0.25 | 0.25 | 100% | High | Waylon | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | LD Meeting - Improving Workflow (Level Streaming) | 0.25 | 0.25 | 100% | High | Wade-Hahn | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Level Lighting Consulting | 0.75 | 0.75 | 100% | Med | Robbie | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Game Design Updates | 0.25 | 0.25 | 100% | High | Robbie | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Game Design/Environment Review | 0.75 | 0.75 | 100% |  | Robbie |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Compile Kleenex Test Report | 1 | cut | n/a | Med | Ben | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Create Weekly DVD Backup | 0.5 | 0.5 | 100% | High | Loren | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Create Weekly DVD Backup | 0.5 | 0.5 | 100% | High | Loren | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Production | Update LD Tasks for Rich | 0.25 | 0.25 | 100% | High | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Update LD Tasks for Rich | 0.25 | 0.25 | 100% | High | Wade-Hahn | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Update LD Backlog and Scrum Board | 2 | 2 | 100% | High | Rich | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Update Programming Backlog and Scrum Board | 1 | 1 | 100% | High | Loren | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 8 (From Alpha) | 0.25 | 0.5 | 50% | Low | Chris | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 1 | 1 | 0.75 | 133.3% | Low | Chris | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 2 | 1 | 0.5 | 200% | Low | Chris | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 3 | 1 | 0.75 | 133.3% | Low | Chris | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 4 | 1 | 0.75 | 133.3% | Low | Chris | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 5 | 1 | 0.5 | 200% | Low | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 6 | 1 | 0.75 | 133.3% | Low | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Production | Calculate Remaining Effort - Day 7 | 1 | 0 | n/a | Low | Chris | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Production | Calculate Remaining Effort - Day 8 | 1 | 0 | n/a | Low | Chris | bar: days in sprint / effort left 0 to days in sprint / effort left 8
Production | Update Product Backlog | 2 | 1 | 200% | Med | Chris | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production | Art Team Meeting, Review and Correct | 2 | cut | n/a | Med | Alex | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Production | Art Team Meeting, Review and Correct | 2 | cut | n/a | Med | Robbie | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Production | Kleenex Test | 0.5 | cut | n/a | Low | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Kleenex Test | 0.5 | cut | n/a | High | Wade-Hahn | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Kleenex Test | 0.5 | cut | n/a | High | Waylon | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Kleenex Test | 0.5 | cut | n/a | High | Ben | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Kleenex Test | 0.5 | cut | n/a | High | Tony | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 2.5 | 20% | High | Chris | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 2.5 | 20% | Low | Alex | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 2.5 | 20% | High | Rich | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 2.5 | 20% | High | Loren | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 2.5 | 20% | High | Robbie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 2.5 | 20% | High | Wade-Hahn | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 2.5 | 20% | High | Waylon | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 2.5 | 20% | High | Ben | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Review | 0.5 | 2.5 | 20% | High | Tony | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Loren | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Tony | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Ben | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Alex | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Rich | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Robbie | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Waylon | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Wade-Hahn | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Production | Sprint Retrospective/Planning Meeting | 1 | 0.5 | 200% | High | Chris | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
http://agilesoftwaredevelopment.com/scrum/simple-sprint-backlog
Note on B1: sprint goal
Note on B208: See for reference and comments. Feel free to remove the link, though it would be very kind of you to leave it somewhere on the sheet

## Alpha
Sprint 4. Alpha
Not Finished/Moved to Next Milestone
days in sprint / effort left
| Tasks | Estimate | Actual | Accuracy | Priority | Assigned To: | 0 | 1 | 2 | 3 | 4
[7 empty] | 110.75 | 93 | 61 | 26 | 2
Programming
Programming | Final installer | 1 | 1 | 100% | High | Loren | 1 | 1 | 1 | 0 | 0
Programming | Gameplay polish | 6 | 8 | 75% | High | Tony | 6 | 6 | 6 | 0 | 0
Programming | AI Polish | 6 | 5 | 120% | High | Ben | 6 | 6 | 6 | 0 | 0
Programming | New HUD graphics | 1.5 | 3 | 50% | High | Loren | 1.5 | 0 | 0 | 0 | 0
Programming | Final main menu | 2 | 1 | 200% | High | Loren | 2 | 2 | 0 | 0 | 0
Programming | New AI | 3 | 5 | 60% | Med | Tony | 3 | 3 | 3 | 0 | 0
Art
Art | Shedu diffuse Texture | 3 | 4 | 75% | High | Alex | 3 | 0 | 0 | 0 | 0
Art | Shedu emissive Texture | 1 | 0.75 | 133.3% | High | Alex | 1 | 0 | 0 | 0 | 0
Art | Shedu alpha Texture | 0.75 | 0.25 | 300% | High | Alex | 0.75 | 0 | 0 | 0 | 0
Art | Collect Screen Shots | 0.75 | 2 | 37.5% | Med | Robbie | 0.75 | 0.75 | 0 | 0 | 0
Art | CD-Label | 2 | 2 | 100% | High | Waylon | 2 | 2 | 0 | 0 | 0
Art | Box Art | 2 | 2.5 | 80% | High | Robbie | 2 | 0 | 0 | 0 | 0
Art | Instruction Manual | 2 | 2 | 100% | High | Waylon | 2 | 2 | 0 | 0 | 0
Art | Controls Menu | 0.75 | 0.25 | 300% | Low | Robbie | 0.75 | 0.75 | 0 | 0 | 0
Art | Controls Menu buttons | 0.75 | 0.25 | 300% | Low | Robbie | 0.75 | 0.75 | 0 | 0 | 0
Art | DVD Art | 1 | 1 | 100% | Low | Waylon |  |  | 0 | 0 | 0
Level Design
Level Design | Environment
Level Design | Scale BSP | 0.5 | 0.5 | 100% | Low | Rich | 0.5 | 0 | 0 | 0 | 0
Level Design | Finish Deco | 2 | 2 | 100% | Med | Rich | 2 | 2 | 0 | 0 | 0
Level Design | Finalize Collision | 0.5 | 0.75 | 66.67% | High | Waylon | 0.5 | 0 | 0 | 0 | 0
Level Design | Deco Training Room | 1 | 1 | 100% | High | Rich | 1 | 0 | 0 | 0 | 0
Level Design | Materials
Level Design | Materials Final Pass | 1 | 0.5 | 200% | Med | Waylon |  |  | 0 | 0 | 0
Level Design | Particle Effects
Level Design | Place Ambient Dust Particle Effect | 0.5 | 0.5 | 100% | High | Rich | 0.5 | 0 | 0 | 0 | 0
Level Design | Boss Death Miasma Particle | 0.25 | 0.5 | 50% | Med | Chris | 0.25 | 0.25 | 0 | 0 | 0
Level Design | Fix Color on Miasma Particles | 2 | 2 | 100% | Med | Chris |  |  | 0 | 0 | 0
Level Design | Fix Urn Smash | 0.25 | 0.25 | 100% | Med | Chris |  |  | 0 | 0 | 0
Level Design | Matinee
Level Design | Polish camera movement and cuts for Intro | 2 | 0.5 | 400% | Low | Wade-Hahn | 2 | 2 | 0 | 0 | 0
Level Design | Polish camera movement and cuts for transition to shadow world | 3 | 0.5 | 600% | Low | Wade-Hahn | 3 | 3 | 0 | 0 | 0
Level Design | Animations, Transition to Shadow World | 2 | 1 | 200% | Med | Wade-Hahn | 2 | 2 | 0 | 0 | 0
Level Design | Camera work, Transition from Shadow mode | 6 | 0.5 | 1200% | High | Wade-Hahn | 6 | 6 | 0 | 0 | 0
Level Design | Animations, Transition from Shadow mode | 3 | 0.5 | 600% | High | Wade-Hahn | 3 | 3 | 0 | 0 | 0
Level Design | Shedu Death | 1 | 1 | 100% | Med | Wade-Hahn | 1 | 1 | 0 | 0 | 0
Level Design | Scripting
Level Design | Fix moon Orb Post-Processing Trigger | 1 | 1 | 100% | High | Waylon | 1 | 0 | 0 | 0 | 0
Level Design | Disable Controls during Cutscene | 2 | not done | n/a | High | Waylon | 2 | 2 | 2 | 2 | 2
Level Design | Hook up Matinees to Game | 1 | 0.5 | 200% | High | Waylon | 1 | 1 | 0 | 0 | 0
Level Design | Lighting
Level Design | Point Light Properties at ASG Quality | 0.5 | 0.5 | 100% | Med | Rich | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Spot Light Properties at ASG Quality | 0.5 | 0.5 | 100% | Med | Rich | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Sky Light Properties at ASG Quality | 0.5 | 0.5 | 100% | Med | Rich | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Level Design | Lightmass Settings at ASG Quality | 1 | 1 | 100% | Med | Rich | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sound
Sound | Player Death Music | 1 | cut | n/a | Med | Rich | 1 | 1 | 1 | 0 | 0
Sound | Boss Death Music | 1 | cut | n/a | Med | Rich | 1 | 0 | 0 | 0 | 0
Production
Production | Create Weekly DVD Backup | 0.5 | 0.5 | 100% | High | Loren | 0.5 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 7 (Beta) | 1 | 0.5 | 200% | Low | Chris | 1 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 8 (Beta) | 1 | 0.5 | 200% | Low | Chris | 1 | 0 | 0 | 0 | 0
Production | Compile Backlog Actuals (Beta) | 0.5 | 0.5 | 100% | High | Chris | 0.5 | 0 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 1 | 1 | 0.5 | 200% | Low | Chris | 1 | 1 | 0 | 0 | 0
Production | Calculate Remaining Effort - Day 2 | 1 | 0.5 | 200% | Low | Chris | 1 | 1 | 1 | 0 | 0
Production | Calculate Remaining Effort - Day 3 | 1 | 0.5 | 200% | Low | Chris | 1 | 1 | 1 | 0 | 0
Production | Calculate Remaining Effort - Day 4 | 1 | 0.25 | 400% | Low | Chris | 1 | 1 | 1 | 0 | 0
Production | Update Sprint (RTM) Backlog | 2 | 1 | 200% | High | Chris | 2 | 0 | 0 | 0 | 0
Production | Update GDD | 2 | 10 | 20% | High | Robbie | 2 | 2 | 2 | 0 | 0
Production | Update TDD | 2 | 10 | 20% | High | Loren | 2 | 2 | 2 | 0 | 0
Production | Update LDD | 2 | 4 | 50% | High | Rich | 2 | 2 | 2 | 0 | 0
Production | Update ASG | 2 | 5 | 40% | High | Alex | 2 | 2 | 2 | 0 | 0
Production | Update Product Backlog | 2 | 1 | 200% | Med | Chris | 2 | 2 | 2 | 0 | 0
Production | Update Asset Database | 2 | 2.5 | 80% | Low | Wade-Hahn | 2 | 2 | 2 | 0 | 0
Production | Compile Backlog Actuals (RTM) | 1 | 1 | 100% | High | Chris | 1 | 1 | 1 | 0 | 0
Production | Update ADP | 2 | 3 | 66.67% | High | Chris | 2 | 2 | 2 | 0 | 0
Production | Final Presentations | 3 | 3 | 100% | High | Alex | 3 | 3 | 3 | 3 | 0
Production | Final Presentations | 3 | 3 | 100% | High | Rich | 3 | 3 | 3 | 3 | 0
Production | Final Presentations | 3 | 3 | 100% | High | Wade-Hahn | 3 | 3 | 3 | 3 | 0
Production | Final Presentations | 3 | 3 | 100% | High | Waylon | 3 | 3 | 3 | 3 | 0
Production | Final Presentations | 3 | 3 | 100% | High | Chris | 3 | 3 | 3 | 3 | 0
Production | Final Presentations | 3 | 3 | 100% | High | Loren | 3 | 3 | 3 | 3 | 0
Production | Final Presentations | 3 | 3 | 100% | High | Tony | 3 | 3 | 3 | 3 | 0
Production | Final Presentations | 3 | 3 | 100% | High | Ben | 3 | 3 | 3 | 3 | 0
http://agilesoftwaredevelopment.com/scrum/simple-sprint-backlog
Note on B1: sprint goal
Note on B89: See for reference and comments. Feel free to remove the link, though it would be very kind of you to leave it somewhere on the sheet

## Ideal Burn Calcs
Vertical Slice | Alpha | Beta | Beta
Ideal Velocity | Ideal Velocity | Ideal Velocity | Ideal Velocity
26.25 | 33.775 | 22.4125 | 27.6875
Ideal Burndown | Ideal Burndown | Ideal Burndown | Ideal Burndown
183.75 | 270.2 | 179.3 | 110.75
157.5 | 236.425 | 156.8875 | 83.0625
131.25 | 202.65 | 134.475 | 55.375
105 | 168.875 | 112.0625 | 27.6875
78.75 | 135.1 | 89.65 | 0
52.5 | 101.325 | 67.2375
26.25 | 67.55 | 44.825
0 | 33.775 | 22.4125
| 0 | 3.5527e-14